## Cover Page
MANUAL TESTING PROJECT
ShopEase — E-Commerce Web Application
Module: User Authentication & Checkout Flow
Project Name | ShopEase E-Commerce Platform
Version | v2.1.0
Testing Type | Functional ¦ Regression ¦ UI ¦ Negative
Test Environment | Chrome 124, Firefox 125, Edge (Windows 11)
Test Duration | 2 Weeks (10 Working Days)
Tester Name | QA Engineer
Test Manager | Self-directed Project
Start Date | 01-May-2025
End Date | 14-May-2025
Report Date | 15-May-2025
Total TCs | 42
Bugs Found | 14 (3 Critical, 5 High, 4 Medium, 2 Low)
Pass Rate | 80% (28 / 35 Executed)
Overall Status | ⚠ Blocked — 3 Critical Bugs Open
CONFIDENTIAL — QA Testing Portfolio Project

## Test Plan
TEST PLAN DOCUMENT — ShopEase v2.1.0
1. Project Information
Project Name | ShopEase — E-Commerce Web Application
Application URL | https://shopease-demo.com (UAT Environment)
Version Under Test | v2.1.0
Prepared By | QA Engineer
Review Date | 15-May-2025
2. Objective
To verify that all user-facing features of ShopEase work as per requirements, are free from critical defects, and meet the defined acceptance criteria before production deployment.
3. Scope of Testing
IN SCOPE | User Registration, Login / Logout, Forgot Password, Add to Cart, Remove from Cart, Apply Coupon, Checkout Flow, Order Confirmation, Input Validations, Error Messages, Session Management
OUT OF SCOPE | Payment Gateway Integration, Admin Panel, Performance / Load Testing, API Testing, Mobile App
4. Test Environment
Operating System | Windows 11 Pro (64-bit) ¦ Android 13
Browsers | Google Chrome 124 ¦ Mozilla Firefox 125 ¦ Microsoft Edge
Test Data | Manually created test accounts and dummy order data
Bug Tracking Tool | JIRA (simulated) — Bug IDs: BUG-001 to BUG-014
Test Mgmt Tool | MS Excel / Google Sheets
Screenshot Tool | Snagit ¦ Lightshot
DevTools | Chrome DevTools — Console, Network, Application tabs
5. Test Design Techniques Used
Equivalence Partitioning | Divided input ranges into valid/invalid partitions (e.g., password length: <8, 8-20, >20)
Boundary Value Analysis | Tested edge values: min (8 chars), max (20 chars) for password field
Negative Testing | Tested invalid email formats, SQL injection, empty fields, expired coupons
Exploratory Testing | Unscripted sessions to discover unexpected behavior in checkout flow
Regression Testing | Re-tested fixed bugs to confirm no new issues introduced
6. Entry & Exit Criteria
Entry Criteria | Build deployed to UAT, test environment accessible, test data ready, requirements documented
Exit Criteria | ≥80% test cases executed ¦ ≥75% pass rate ¦ 0 Critical bugs open ¦ All requirements covered
7. Risks & Mitigations
Risk: Incomplete requirements | Mitigation: Clarified gaps with developer; documented assumptions in test cases
Risk: Unstable test environment | Mitigation: Tested in Chrome first; re-ran failures on Firefox/Edge to isolate browser bugs
Risk: Time constraint (2 weeks) | Mitigation: Prioritized High/Critical paths first; deferred low-risk edge cases

## Test Cases
TEST CASES — ShopEase v2.1.0 ¦ Modules: Login ¦ Register ¦ Checkout ¦ Cart ¦ Profile
TC ID | Module | Test Case Title | Test Type | Steps to Execute | Test Data | Expected Result | Actual Result | Status
TC-LG-01 | Login | Valid login with registered credentials | Positive | 1. Open login page 2. Enter valid email: test@mail.com 3. Enter correct password: Test@1234 4. Click 'Login' button | Email: test@mail.com Password: Test@1234 | User redirected to homepage; welcome message shown; session cookie created | User logged in successfully; homepage displayed | Pass
TC-LG-02 | Login | Login with incorrect password | Negative | 1. Open login page 2. Enter valid email 3. Enter wrong password: Wrong123 4. Click 'Login' | Email: test@mail.com Password: Wrong123 | Error message: 'Invalid email or password' displayed; user stays on login page | Error message shown correctly | Pass
TC-LG-03 | Login | Login with unregistered email | Negative | 1. Enter email not in DB: notexist@x.com 2. Enter any password 3. Click 'Login' | Email: notexist@x.com | Error: 'Account not found. Please register.' | Error displayed as expected | Pass
TC-LG-04 | Login | Login with all fields empty | Negative | 1. Leave email and password blank 2. Click 'Login' | Empty fields | Validation error on both fields; form not submitted | Both field errors shown | Pass
TC-LG-05 | Login | Login with invalid email format | Negative | 1. Enter 'user@' in email field 2. Enter any password 3. Click 'Login' | Email: user@ | Inline validation: 'Please enter a valid email address' | No frontend validation triggered; request sent to server; 400 error not handled | Fail
TC-LG-06 | Login | 'Remember Me' session persistence | Functional | 1. Check 'Remember Me' 2. Login successfully 3. Close browser 4. Reopen & visit site | Email/Password: valid | User remains logged in; session persists after browser close | Session expired; user logged out | Fail
TC-LG-07 | Login | Logout clears session | Functional | 1. Login successfully 2. Click profile avatar > 'Logout' 3. Try to access /dashboard directly | N/A | Session terminated; redirect to login page; /dashboard inaccessible | Logged out; dashboard access blocked | Pass
TC-LG-08 | Login | Password field masking | UI | 1. Open login page 2. Type password in password field 3. Observe field display | Password: Test@1234 | Password displayed as dots/asterisks throughout typing | Password masked correctly | Pass
TC-LG-09 | Login | Forgot Password link visible | UI | 1. Open login page 2. Check for 'Forgot Password?' link | N/A | 'Forgot Password?' link is visible and clickable | Link visible; redirects to password reset page | Pass
TC-LG-10 | Login | Brute force — 5 failed attempts | Security | 1. Enter wrong password 5 consecutive times | Wrong password ×5 | Account temporarily locked; CAPTCHA or lockout message shown | No lockout triggered; unlimited attempts allowed | Fail
TC-RG-01 | Register | Register with valid data | Positive | 1. Fill all fields with valid data 2. Click 'Register' | Name: Rk Sharma Email: newuser@mail.com Phone: 9876543210 Password: Secure@123 | Account created; redirect to homepage; welcome email sent | Account created successfully | Pass
TC-RG-02 | Register | Register with existing email | Negative | 1. Enter already-registered email 2. Complete form & submit | Email: test@mail.com (existing) | Error: 'Email already in use. Try logging in.' | Second account created silently; no error displayed | Fail
TC-RG-03 | Register | Password shorter than 8 characters | Negative | 1. Enter password with 6 characters: abc123 2. Submit form | Password: abc123 | Inline error: 'Password must be at least 8 characters' | Validation error shown correctly | Pass
TC-RG-04 | Register | Password & confirm password mismatch | Negative | 1. Enter Password: Test@1234 2. Enter Confirm Password: Test@5678 3. Submit | Mismatched passwords | Error: 'Passwords do not match' | Error shown correctly | Pass
TC-RG-05 | Register | SQL injection in name field | Security | 1. Enter: '; DROP TABLE users;-- in name field 2. Submit form | Name: '; DROP TABLE users;-- | Input sanitized; no DB error; graceful validation message shown | Application throws 500 DB error; potential data loss | Fail
TC-RG-06 | Register | Alphabets in phone number field | Negative | 1. Enter 'abc' in phone field 2. Submit | Phone: abc | Error: 'Please enter a valid 10-digit phone number' | Validation error shown correctly | Pass
TC-RG-07 | Register | All fields left blank | Negative | 1. Submit registration form without filling any field | Empty form | Validation errors shown on all required fields | All field errors displayed | Pass
TC-RG-08 | Register | XSS script in input field | Security | 1. Enter <script>alert('XSS')</script> in name field 2. Submit | Name: <script>alert('XSS')</script> | Script tag stripped/escaped; no alert popup; data sanitized | Script tag stored but escaped on display; no execution | Pass
TC-CK-01 | Checkout | Checkout with items in cart | Positive | 1. Login 2. Add item to cart 3. Proceed to checkout 4. Fill delivery address 5. Place order | Valid item, address, payment | Order placed; unique order ID generated; confirmation email sent | Order confirmed but email not received | Fail
TC-CK-02 | Checkout | Checkout with empty cart | Negative | 1. Login 2. Navigate directly to /checkout with empty cart | Empty cart | Redirect to cart page: 'Your cart is empty. Add items to continue.' | Redirected with correct message | Pass
TC-CK-03 | Checkout | Apply valid coupon code | Functional | 1. Add item to cart (₹1000) 2. Apply coupon: SAVE20 3. Check updated total | Coupon: SAVE20 (20% off) | 20% discount applied; total shows ₹800 | Not Executed | Not Run
TC-CK-04 | Checkout | Apply expired coupon code | Negative | 1. Add item to cart 2. Apply coupon: OLD10 | Coupon: OLD10 (expired) | Error: 'Coupon code expired or invalid' | Expired coupon accepted; 10% discount applied incorrectly | Fail
TC-CK-05 | Checkout | Remove item from cart | Functional | 1. Add 2 items to cart 2. Remove 1 item 3. Check cart count and total | 2 items in cart | Item removed; cart count = 1; total recalculated without page refresh | Cart count updates but total doesn't recalculate until page refresh | Fail
TC-CK-06 | Checkout | Quantity increment/decrement | Functional | 1. Add item to cart 2. Increase quantity to 3 3. Check total | Item price: ₹500 | Total = ₹1500; cart count updates dynamically | Total updates correctly | Pass
TC-CK-07 | Checkout | Order placed without login | Security | 1. Logout 2. Add item via direct URL manipulation 3. Navigate to /checkout | Logged-out user | Redirect to login page; checkout not accessible without authentication | Redirected to login correctly | Pass
TC-PF-01 | Profile | View profile page after login | Functional | 1. Login 2. Click avatar > 'My Profile' | Logged-in user | Profile page shows name, email, order history correctly | Profile loaded correctly | Pass
TC-PF-02 | Profile | Edit profile — update phone number | Functional | 1. Go to profile 2. Click Edit 3. Update phone: 9999988888 4. Save | New phone: 9999988888 | Profile updated; success toast shown; new number reflected | Profile updated successfully | Pass
TC-PF-03 | Profile | Access profile page without login via URL | Security | 1. Logout 2. Enter /profile URL directly | Logged-out user | Redirect to login page immediately | Profile page partially loaded with blank data (Bug Fixed) | Pass
TC-PF-04 | Profile | Order history visible on profile | Functional | 1. Place 1 order 2. Go to profile > 'My Orders' | 1 completed order | Order ID, date, amount, status visible in order history | Order history displayed correctly | Pass

## Bug Reports
BUG REPORTS — ShopEase v2.1.0 ¦ Total: 14 Bugs ¦ Critical: 3 ¦ High: 5 ¦ Medium: 4 ¦ Low: 2
Bug ID | Module | Bug Title | Environment | Severity | Steps to Reproduce | Expected Result | Actual Result / Observed | Status | Priority
BUG-001 | Register | SQL Injection not sanitized in Name field | Chrome 124 | Critical | 1. Go to Register page 2. Enter: '; DROP TABLE users;-- in First Name 3. Fill other fields normally 4. Click Submit | Input rejected or sanitized; graceful error message shown | Application throws HTTP 500 Database error; partial data inserted into DB; potential data loss | Open | P1
BUG-002 | Register | Duplicate email allows second account creation | Chrome 124 | Critical | 1. Register with email: test@mail.com 2. Logout 3. Register again with same email 4. Click Submit | Error: 'Email already in use. Try logging in.' | Second account created silently; no error shown; both records visible in DB | Open | P1
BUG-003 | Checkout | Expired coupon code applies discount without error | Chrome 124 | Critical | 1. Add item to cart 2. Enter expired coupon code: OLD10 3. Click Apply | Error: 'Coupon code has expired or is invalid' | 10% discount applied incorrectly; no error shown; wrong order total displayed | Open | P1
BUG-004 | Login | Invalid email format accepted at login | Firefox 125 | High | 1. Open login page 2. Enter 'user@' in email field 3. Enter any password 4. Click Login | Frontend validation: 'Please enter a valid email address' | No client-side validation; request sent to server; 400 error not handled gracefully | Fixed | P2
BUG-005 | Cart | Cart total not updated after item removal | Chrome 124 | High | 1. Add 3 items to cart 2. Click Remove on 1 item 3. Check displayed cart total immediately | Total should update in real-time to reflect 2 items | Total remains unchanged until full page refresh; UI out of sync with cart state | Open | P2
BUG-006 | Login | Password temporarily visible in plain text on double-click | Chrome 124 | High | 1. Open login page 2. Type password in password field 3. Double-click on the password field | Password remains masked at all times | Password briefly shown as plain text on double-click in Chrome 124 | Open | P2
BUG-007 | Checkout | Order confirmation email not sent after successful checkout | Chrome 124 | High | 1. Login with valid user 2. Add item to cart 3. Complete checkout with valid address 4. Wait 5 minutes | Confirmation email received within 2 minutes | No email received; checked inbox and spam; order visible in profile but no email | Open | P2
BUG-008 | Login | 'Remember Me' session not persisting after browser close | Chrome 124 | High | 1. Login with 'Remember Me' checked 2. Close browser completely 3. Reopen browser 4. Navigate to site | User session persists; user remains logged in | User logged out; session not retained despite checking 'Remember Me' | Open | P2
BUG-009 | Profile | Profile page accessible without authentication via direct URL | Chrome 124 | Medium | 1. Logout from account 2. Type /profile URL directly in browser 3. Press Enter | Immediate redirect to login page | Profile page loads partially with blank user data; no authentication check or redirect | Fixed | P2
BUG-010 | Login | No account lockout after 5 failed login attempts | Chrome 124 | Medium | 1. Enter wrong password 5 times consecutively for same account 2. Observe response on 5th attempt | Account locked temporarily; CAPTCHA triggered or lockout message shown | No lockout mechanism; unlimited login attempts allowed; brute force possible | Open | P2
BUG-011 | Register | Error message not shown when password lacks special character | Chrome 124 | Medium | 1. Register with password: TestPass1 (no special char) 2. Submit form | Error: 'Password must contain at least 1 special character' | Account created successfully; no validation for special character requirement | Open | P3
BUG-012 | Checkout | 'Place Order' button remains clickable on network failure | Chrome 124 | Medium | 1. Add item to cart 2. Simulate offline (DevTools > Network > Offline) 3. Click 'Place Order' | Button disabled or error: 'Network error. Please check your connection.' | Button remains active; multiple POST requests queued; duplicate orders possible | Open | P3
BUG-013 | Global UI | Toast notification overlaps footer on mobile viewport | Chrome Mobile | Low | 1. Open site on 375px viewport 2. Trigger any success or error toast notification 3. Observe position | Toast appears within safe area above navigation | Toast partially hidden behind mobile browser bottom navigation bar | Won't Fix | P4
BUG-014 | Profile | Phone number field allows more than 10 digits | Chrome 124 | Low | 1. Go to Edit Profile 2. Enter phone: 99999888887777 3. Save | Validation: 'Phone must be exactly 10 digits' | Phone saved with 14 digits; no max-length validation on frontend | Open | P4

## RTM
REQUIREMENTS TRACEABILITY MATRIX (RTM) — ShopEase v2.1.0
Req ID | Requirement Description | Linked Test Cases | Execution Status | Pass / Fail | Defect IDs | Req. Status
REQ-01 | User shall register with a unique email address and a secure password | TC-RG-01, TC-RG-02, TC-RG-03, TC-RG-04, TC-RG-07 | Executed | 3 Pass / 1 Fail | BUG-001, BUG-002 | At Risk
REQ-02 | System shall validate and reject malicious or invalid input data | TC-RG-05, TC-RG-08, TC-LG-05 | Executed | 1 Pass / 2 Fail | BUG-001, BUG-004 | At Risk
REQ-03 | Registered user shall log in using correct credentials | TC-LG-01, TC-LG-02, TC-LG-03, TC-LG-04 | Executed | 4 Pass / 0 Fail | — | Passed
REQ-04 | User shall be able to log out and session shall be terminated | TC-LG-07 | Executed | 1 Pass / 0 Fail | — | Passed
REQ-05 | System shall support 'Remember Me' for persistent sessions | TC-LG-06 | Executed | 0 Pass / 1 Fail | BUG-008 | Failed
REQ-06 | System shall prevent brute-force login attacks | TC-LG-10 | Executed | 0 Pass / 1 Fail | BUG-010 | Failed
REQ-07 | User shall be able to add items and see correct cart total | TC-CK-05, TC-CK-06 | Executed | 1 Pass / 1 Fail | BUG-005 | At Risk
REQ-08 | Valid coupons shall apply discount; expired coupons shall be rejected | TC-CK-03, TC-CK-04 | Partial | 0 Pass / 1 Fail | BUG-003 | Failed
REQ-09 | Order confirmation email shall be sent within 2 minutes of checkout | TC-CK-01 | Executed | 0 Pass / 1 Fail | BUG-007 | Failed
REQ-10 | Protected pages shall redirect unauthenticated users to login | TC-CK-07, TC-PF-03 | Executed | 2 Pass / 0 Fail | BUG-009 (Fixed) | Passed
REQ-11 | User shall be able to view and edit profile information | TC-PF-01, TC-PF-02, TC-PF-04 | Executed | 3 Pass / 0 Fail | — | Passed
REQ-12 | Password shall meet strength requirements (min 8 chars, special char) | TC-RG-03, TC-RG-04 | Executed | 1 Pass / 1 Fail | BUG-011 | At Risk

## Test Metrics
TEST EXECUTION METRICS & SUMMARY — ShopEase v2.1.0
42 | 35 | 28 | 7 | 7 | 14 | 3 | 2 | 12/12
Total Test Cases | Executed | Passed | Failed | Not Run | Bugs Found | Critical Bugs | Bugs Fixed | Req. Covered
Written | 83% coverage | 80% pass rate | 20% fail rate | Pending | Total defects | Blockers | 14% fix rate | 100%
Execution Summary by Module
Module | Total TCs | Executed | Passed | Failed | Not Run | Pass Rate | Bugs Found
Login | 10 | 10 | 7 | 3 | 0 |  | 5
Register | 8 | 8 | 5 | 3 | 0 |  | 4
Checkout | 10 | 9 | 5 | 3 | 1 |  | 5
Cart | 4 | 4 | 3 | 1 | 0 |  | 1
Profile | 6 | 4 | 4 | 0 | 2 |  | 0
Global UI | 4 | 0 | 4 | 0 | 4 |  | 1
TOTAL | 42 | 35 | 28 | 7 | 7 |  | 14
Defect Summary by Severity
Severity | Count | Open | Fixed / Won't Fix
Critical | 3 | 3 | 0
High | 5 | 4 | 1
Medium | 4 | 3 | 1
Low | 2 | 0 | 2
TOTAL | 14 | 10 | 4
Exit Criteria Checklist
Criteria | Target | Achieved | Met? | Comments
Test case execution | ≥ 80% | 83% | ✔ Met | 7 test cases pending — low priority
Overall pass rate | ≥ 75% | 80% | ✔ Met | Within acceptable threshold
Zero open Critical bugs | 0 Critical | 3 Critical | ✘ Not Met | BUG-001, BUG-002, BUG-003 open — BLOCKS GO-LIVE
All requirements tested | 100% | 100% | ✔ Met | All 12 requirements mapped to test cases
Regression of fixed bugs | All fixed = Pass | 2/2 Verified | ✔ Met | BUG-004 and BUG-009 re-verified
Sign-off recommendation | Pass all criteria | 3 criteria met | ⚠ HOLD | Recommend blocking deployment until Critical bugs resolved